The Norwegian Real Estate Terminal — Execution Plan

Context

TerraGIS AS wants to build a Bloomberg-class real estate intelligence platform for Norwegian markets. The 303-line architecture blueprint specifies: 35+ risk measures via Riskfolio-lib, 7 free Norwegian government APIs, Medallion data architecture on Azure Norway East, and Bloomberg-style dark-theme UI with portfolio management, stress testing, and spatial risk overlays. No existing Norwegian platform combines these capabilities.

The platform will be built as a new app (apps/terragis-terminal/) in the easy-sandbox repo at https://github.com/EasyEiendom/easy-sandbox.git, following the same custom-template pattern used by the mirofish app (Python backend + JS frontend, single Dockerfile, port 3000).

Claude Code is the main orchestrator. Other AI tools (Cursor, Codex, Grok, Gemini, ChatGPT, Perplexity, Manus) will be given task-specific prompts. A shared CLAUDE.md ensures all tools follow the same conventions.

Phase 1 — MVP: Market Data Terminal (Weeks 1-4)

Goal: A deployed Bloomberg-styled dark-theme dashboard showing Norwegian housing market data from free public APIs. No database, no authentication, no commercial data.

Week 1: Scaffold + Infrastructure

| # | Task | Key Files |
| --- | --- | --- |
| 1 | Clone easy-sandbox, create branch terragis-terminal/initial-mvp | — |
| 2 | Create apps/terragis-terminal/sandbox.yaml | sandbox.yaml (template: custom, port: 3000, cpu: 1.0, memory: 2Gi) |
| 3 | Create multi-stage Dockerfile (Node 22 builds frontend, Python 3.11-slim runs backend via FastAPI/uvicorn on port 3000) — follow mirofish pattern exactly | Dockerfile |
| 4 | Initialize frontend: Vite + React 19 + TypeScript + Tailwind CSS 4 | frontend/package.json, frontend/vite.config.ts, frontend/tsconfig.json |
| 5 | Initialize backend: FastAPI + uvicorn + httpx + pydantic | backend/pyproject.toml, backend/app/main.py |
| 6 | Wire up: FastAPI serves built Vite output as static files + /api/* routes | backend/app/main.py |
| 7 | Write CLAUDE.md for cross-tool coordination (see below) | CLAUDE.md |
| 8 | Verify: docker build + docker run → app loads at localhost:3000 | — |

Week 2: Core Data Pipelines (SSB + Norges Bank)

| # | Task | Key Files |
| --- | --- | --- |
| 9 | ssb_client.py: POST queries to data.ssb.no/api/v0/no/table/{id}, JSON-stat v1.2 response parser, in-memory TTL cache | backend/app/services/ssb_client.py |
| 10 | norgesbank_client.py: SDMX-JSON parser for policy rate + NOWA (dimension-indexed series resolution) | backend/app/services/norgesbank_client.py |
| 11 | API routes: /api/ssb/price-index, /api/rates/policy, /api/rates/nowa | backend/app/api/ssb.py, backend/app/api/norgesbank.py |
| 12 | PriceIndexChart.tsx: TradingView Lightweight Charts, multi-region overlay, region + dwelling type selectors | frontend/src/components/charts/PriceIndexChart.tsx |
| 13 | InterestRateChart.tsx: Policy rate history chart | frontend/src/components/charts/InterestRateChart.tsx |

SSB Tables for Phase 1:

- 07221: Housing price index by region + dwelling type (quarterly, 1992-present)

- 08654/08655: Construction cost index (annual/monthly)

- 14696/14697: Harmonized CPI (monthly/annual)

- 10748/10738: Interest rates on dwelling loans (monthly)

- 06266: Dwellings by building type + construction year (annual)

Norges Bank endpoints:

- IR/B.KPRA.. — Policy rate (styringsrenten)

- SHORT_RATES/B.NOWA+NOWA_AVERAGE.ON+6M+3M+1M+1D. — NOWA rate

- REGNET/ — Regional Network (quarterly)

Week 3: Extended Data + Tables + Status

| # | Task | Key Files |
| --- | --- | --- |
| 14 | Add remaining SSB table clients (construction costs, CPI, dwelling stats, mortgage rates) | backend/app/api/ssb.py (extend) |
| 15 | DataGrid.tsx: AG Grid Community wrapper — sortable, filterable tables for raw SSB data | frontend/src/components/tables/DataGrid.tsx |
| 16 | MarketSummary.tsx: Card with latest values (HPI, policy rate, CPI, construction cost index) | frontend/src/components/widgets/MarketSummary.tsx |
| 17 | StatusBar.tsx: Data freshness indicators (green=today, yellow=this week, red=stale) | frontend/src/components/layout/StatusBar.tsx |

Week 4: Maps + Search + Shell + Deploy

| # | Task | Key Files |
| --- | --- | --- |
| 18 | nve_client.py: ArcGIS REST queries to gis3.nve.no for flood zones (7 return periods), handle 1000-record limit | backend/app/services/nve_client.py |
| 19 | Geonorge address search proxy: ws.geonorge.no/adresser/v1/sok | backend/app/api/geonorge.py |
| 20 | FloodZoneMap.tsx: Leaflet + Geonorge WMS basemap + NVE flood zone WMS overlay (togglable by return period) | frontend/src/components/maps/FloodZoneMap.tsx |
| 21 | PropertyLookup.tsx: Address search → geocode → center map | frontend/src/pages/PropertyLookup.tsx |
| 22 | Shell.tsx: Dark theme (bg-gray-950), left sidebar nav, resizable panel layout | frontend/src/components/layout/Shell.tsx |
| 23 | CommandBar.tsx: Ctrl+K command palette, fuzzy search across pages | frontend/src/components/layout/CommandBar.tsx |
| 24 | Deploy: PR to master → auto-deploy via GitHub Actions | — |

Phase 1 Frontend Dependencies

react, react-dom, @tanstack/react-query, lightweight-charts (TradingView),

leaflet, react-leaflet, ag-grid-community, ag-grid-react,

tailwindcss, @headlessui/react, lucide-react, react-router-dom

Phase 1 Backend Dependencies

fastapi, uvicorn[standard], httpx, pydantic, pydantic-settings

Phase 2 — Risk Analytics Engine (Months 2-4)

Goal: Portfolio construction, 35+ quantitative risk measures, stress testing, Norwegian regulatory compliance.

Month 2: Portfolio + Risk Measures

| # | Task |
| --- | --- |
| 25 | Add riskfolio-lib, PyPortfolioOpt, numpy, scipy, pandas to backend |
| 26 | risk_engine.py: Wraps Riskfolio-lib — input: portfolio weights across regions/dwelling types; data: quarterly returns from SSB 07221; output: CVaR, CDaR, MDD, Semi-SD, Ulcer Index, GMD |
| 27 | HRP optimization: Auto-cluster correlated property markets via HCPortfolio(codependence='pearson', linkage='ward') |
| 28 | Portfolio.tsx page: Allocation editor (sliders per region), risk metrics display, efficient frontier chart |

Month 2-3: Stress Testing

| # | Task |
| --- | --- |
| 29 | stress_scenarios.py: 6 pre-built Norwegian scenarios — interest rate +300bp, oil crash -50%, housing bubble -25%, NOK depreciation -20%, rural population decline, climate/flood event |
| 30 | Petroleum correlation model: VAR incorporating Brent crude, Rogaland unemployment, regional income, Stavanger HPI with 2-3 quarter lag |
| 31 | StressTest.tsx page: Scenario selector, before/after portfolio comparison, region heatmap |

Month 3: Black-Litterman + Fellesgjeld

| # | Task |
| --- | --- |
| 32 | Black-Litterman implementation: port.blacklitterman_stats(P, Q) — user inputs views like "Stavanger underperforms Oslo by 3%" |
| 33 | Fellesgjeld factor model: High shared debt → negative IR factor coefficients (-0.8 to -1.2); selveier → weaker sensitivity (-0.2 to -0.3) |
| 34 | Portfolio exposure constraint: max 30% high-fellesgjeld via assets_constraints() |

Month 4: Regulatory Compliance

| # | Task |
| --- | --- |
| 35 | compliance.py: Utlansforskriften checker (Dec 2024 amendment) — LTV 90%, DTI 5x, stress test current+3pp floor 7%, amortization >60% LTV |
| 36 | tax_calculator.py: Formueskatt — primaerbolig 25%/70%, sekundaerbolig 100%, bunnfradrag 1.9M/person, rates 1.0%/1.1% |
| 37 | Compliance.tsx page: Interactive calculators for LTV/DTI/stress test and wealth tax |

Phase 2 Additional Data Sources

- EasyCore API (pre-configured: EASY_API_CORE_URL + EASY_API_CORE_KEY)

- Geodata REST (credentials: mathiaseasy / 700575ba-7e3a-4bf9-a1a8-4ce330f8087b)

- Norges Bank Regional Network (REGNET/) for economic sentiment per region

Phase 3 — Property Intelligence (Months 5-9)

Goal: Individual property analysis, cadastral data, DCF valuation, spatial risk scoring.

| # | Milestone |
| --- | --- |
| 38 | Maskinporten OAuth2 integration for Kartverket Matrikkelen |
| 39 | Property lookup by Gnr/Bnr/Festenr/Seksjonsnr with cadastral data + building details |
| 40 | DCF valuation engine: KPI-justering (SSB CPI), prime yields by city, WACC with formueskatt adjustment |
| 41 | PostGIS spatial database (SRID 25833/25832) — requires dedicated infrastructure beyond sandbox |
| 42 | Composite risk score: flood exposure + IR sensitivity + fellesgjeld ratio + geographic concentration (HHI) |
| 43 | Silver Databricks queries: registerenhet, eierforhold, heftelser, rettsstiftelser |
| 44 | PropertyDetail.tsx page: Full property profile with boundary polygon on map |

Blocking dependency: Maskinporten application to Kartverket (submit ASAP — approval takes weeks).

Phase 4 — Market Leadership (Months 10-24)

| # | Milestone |
| --- | --- |
| 45 | Commercial data licensing: Eiendomsverdi (AVM/transactions), Norkart (ROS/boundaries) |
| 46 | WebSocket real-time updates via Redis Pub/Sub |
| 47 | JP Morgan Perspective (FINOS) for streaming in-browser analytics |
| 48 | AG Grid Enterprise for advanced table features |
| 49 | QuantLib: Hull-White Monte Carlo for mortgage rate path simulation |
| 50 | Automated Meglerpakke ordering + OCR/NLP extraction |
| 51 | Multi-user auth + RBAC |
| 52 | DPIA completion, Datatilsynet consultation |
| 53 | PRODUCTION-READY.md handoff → dedicated Azure infrastructure |

App Directory Structure

apps/terragis-terminal/

CLAUDE.md                     # Cross-tool coordination

README.md

sandbox.yaml                  # template: custom, port: 3000, cpu: 1.0, memory: 2Gi

Dockerfile                    # Multi-stage: Node 22 build + Python 3.11-slim runtime

.env.example

.gitignore

frontend/

package.json

vite.config.ts

tsconfig.json

index.html

src/

main.tsx

App.tsx

index.css              # Tailwind dark theme globals

components/

layout/Shell.tsx, CommandBar.tsx, StatusBar.tsx, Panel.tsx

charts/PriceIndexChart.tsx, InterestRateChart.tsx, RegionComparison.tsx

tables/DataGrid.tsx

maps/FloodZoneMap.tsx, PropertyMap.tsx

widgets/MarketSummary.tsx, FreshnessIndicator.tsx

hooks/useSSBData.ts, useNorgesBank.ts, useNVE.ts

lib/api.ts, theme.ts

types/index.ts

pages/Dashboard.tsx, MarketData.tsx, RiskMap.tsx, PropertyLookup.tsx

backend/

pyproject.toml

run.py

app/

__init__.py

main.py                # FastAPI app factory + static file serving

config.py              # Pydantic settings from env vars

api/

router.py, ssb.py, norgesbank.py, nve.py, geonorge.py, health.py

services/

ssb_client.py, norgesbank_client.py, nve_client.py, cache.py

models/

schemas.py

Phase 2 adds: api/portfolio.py, api/stress.py, api/compliance.py, services/risk_engine.py, services/stress_scenarios.py, services/compliance.py, services/tax_calculator.py, pages/Portfolio.tsx, pages/StressTest.tsx, pages/Compliance.tsx

CLAUDE.md for Cross-Tool Coordination

The apps/terragis-terminal/CLAUDE.md will contain these sections:

- Quick Start — cd frontend && npm install && npm run dev (port 5173) + cd backend && uv sync && uv run python run.py (port 3000). Vite proxies /api/* to backend.

- Architecture — React 19 + TypeScript + Vite frontend, FastAPI Python backend, no database in Phase 1-2.

- Conventions — All API routes under /api/; frontend never calls external APIs directly; Pydantic models for all schemas; TypeScript strict mode, no any; Tailwind only; chart library: lightweight-charts; map: leaflet + react-leaflet; grid: ag-grid-community; data fetching: @tanstack/react-query.

- Data Source Reference — Exact URLs, table IDs, response format notes for SSB, Norges Bank, NVE, Geonorge.

- File Ownership — Maps directories to purposes so agents avoid conflicts.

- Deployment — sandbox.yaml values, env vars, branch naming terragis-terminal/{feature}, PR flow.

- Phase Roadmap — Current phase, what's built, what's next.

This same file serves Claude Code, Cursor (.cursor/rules/ symlink), Codex, and Copilot.

Multi-Tool Task Delegation

When delegating to other AI tools, give them this context + specific task:

| Tool | Best For | Example Task |
| --- | --- | --- |
| Cursor | Frontend components with live preview | "Build Shell.tsx with dark theme, resizable panels, left sidebar nav" |
| Codex | Backend services, data parsing | "Implement ssb_client.py with JSON-stat v1.2 parser" |
| ChatGPT/Grok | Research, data format exploration | "Parse this SDMX-JSON response and explain the dimension structure" |
| Perplexity | API documentation lookup | "Find the exact NVE ArcGIS REST endpoint for 200-year flood zones" |
| Gemini | Long-document analysis | "Summarize the key risk factors from the 90 literature papers" |
| Manus | Multi-step web research | "Find all SSB tables related to Norwegian housing and list their update frequencies" |

Each tool receives: (1) the CLAUDE.md file, (2) the specific file(s) to create/modify, (3) clear acceptance criteria.

Critical Dependencies & Risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Maskinporten application delay | Blocks Phase 3 cadastral data | Submit application NOW, independently of Phase 1 dev |
| Sandbox resource ceiling (1 CPU / 2Gi) | Cannot run PostGIS + TimescaleDB in Phase 3 | Start conversation with platform team during Phase 2 |
| SSB JSON-stat parsing complexity | Wrong data in charts | Build robust parser with unit tests in Week 2 |
| Norges Bank SDMX dimension indexing | Incorrect rate data | Test parser against known rate values |
| NVE 1000-record limit | Incomplete flood data | Implement bounding-box pagination |
| Riskfolio-lib adds ~200MB to Docker image | Longer build times (~5min) | Acceptable; multi-stage build keeps runtime lean |
| AG Grid Enterprise license | Missing advanced table features | Community edition sufficient through Phase 3 |

Verification Plan

Phase 1 Automated Checks

- cd frontend && npm run build — exits 0, no TypeScript errors

- cd backend && uv run python -c "from app.main import create_app; create_app()" — exits 0

- docker build -t terragis-terminal . — succeeds

- GET /api/health → 200

- GET /api/ssb/price-index?region=TOTAL&type=00&from=2020K1 → JSON with quarterly values

- GET /api/rates/policy → JSON with date-value pairs

- GET /api/flood/zones?lat=59.91&lng=10.75&radius=500 → GeoJSON

- GET /api/address/search?q=Storgata+1+Oslo → address results with coordinates

Phase 1 Manual Checks

- Dark theme loads (bg-gray-950)

- HPI chart renders with 12 SSB regions selectable

- Dwelling type dropdown filters chart

- Interest rate chart shows policy rate history

- AG Grid table shows sortable/filterable data

- Flood zone map loads with Geonorge basemap + NVE overlay

- Return period toggle works (10yr through 1000yr)

- Address search centers map

- Command bar opens on Ctrl+K

- Data freshness indicators show correct states

- After PR merge: app accessible at sandbox.easyeiendom.no

Phase 2 Verification

- Equal-weight portfolio across 4 cities produces CVaR/CDaR values

- HRP optimization returns weights summing to 1.0

- +300bp stress scenario shows negative impact, Stavanger worst

- Black-Litterman shifts weights per user views

- Utlansforskriften: 91% LTV flagged, 89% passes

- Formueskatt: 8M primaerbolig → formuesverdi 2M (25%)

Immediate Next Steps (after plan approval)

- git checkout master && git pull in easy-sandbox

- git checkout -b terragis-terminal/initial-mvp

- Create apps/terragis-terminal/ scaffold (sandbox.yaml, Dockerfile, CLAUDE.md)

- Initialize frontend (Vite + React 19 + TypeScript + Tailwind)

- Initialize backend (FastAPI + uvicorn + httpx)

- Wire up Dockerfile + verify docker build && docker run

- Begin SSB client implementation